## Sprint Goal
Sprint 2 Goal
- Implement the medium layer of abstraction for the project by completing the model package of the project. - Allow a game state instance to be made through some sort of main, and demonstrate that the game processes can complete in a higher level of abstraction. - Make it so game is the highest level of access to every other class in the model package.

## Sprint 1 Backlog
AGILE SPRINT 2 BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
US012: A Player has a Token that they select, board position of their token, Money, a collection of owned properties, and a collection of Mortgaged properties. Players must have a means to accomplish each step of a turn. Player's can mortgage properties even when it is not their turn. Player's must be able to determine the monoplies that they own. They must be able to buy houses and hotel for Properties that belong to a monopoly. The houses and hotels must be evenly distributed among the Properties in a monopoly. Players have an a sequence of steps that they must follow to complete their turn. These steps must be able to change dynamically depending on the Board Space they land on. | 7 | Jon Walsh
Task: determine player class structure, and make a skeleton class containing all necessary functions |  | Jon Walsh | Completed | 1 | 2 | 1 | 0 | 0 | 0 | 0
Task: Implement actions that can occur during players turn. |  | Jon Walsh | Completed | 3 | 3 | 3 | 2 | 1 | 0 | 0
Task: Validation methods for edge cases, and implement Monopoly checking and validation of property distribution |  | Jon Walsh | Completed | 2 | 2 | 2 | 1 | 1 | 0 | 0
Task Make sure all cases are tested 100% methods coverage and full documentation. |  | Jon Walsh | Completed | 1 | 2 | 2.5 | 1.5 | 1 | 0.5 | 0
US015: Player Tokens are a set of objects including Top hat, Thimble, Iron, Boot, Battleship, Cannon, Race car, Scottie dog, Wheelbarrow. Tokens have an owner which is a Player. Each Token should have an icon that represents the token. | 3 | Sean
Task: Make token class |  | Sean | Complete | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
Task: Make all available/choosable tokens |  | Sean | Complete | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Task: Connect a player with their respective token |  | Sean | Complete | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Task: Make icons for the tokens |  | Sean | Complete | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
US001: Each Game Board space must have an action associated with it that controlls what happens when a Player lands on that board space. The Game Board space a Player lands on will determine the steps in the Players turn. | 5 | Sean | Complete
Task: Add strategies and process' for each space |  | Sean | Complete | 2 | 1 | 1 | 0.5 | 0 | 0 | 0
Task: Change GameTile class to appropriate for landOn |  | Sean | Complete | 0.125 | 0 | 0 | 0 | 0 | 0 | 0
Task: Make test to test out fully property landing functionality |  | Sean | Complete | 0.75 | 0.75 | 0.75 | 0.5 | 0 | 0 | 0
US002: A game must have 2 to 4 Players. | 3 | Sydney
Task: Create an if-else statement for Players, coinciding with GameState. If there are less than 2 Players, then the game can’t start. If a 5th Player tries to join it will throw a message/exception saying the player can’t join this round. |  | Sydney | Complete | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Task: Test to check that the restriction on the number of Players works |  | Sydney | Complete | 1 | 1 | 1 | 0 | 0 | 0 | 0
US003: The Banker is not a Player, it a separate entity that is simulated by the program. The Banker has an infinite amount of money, must be able to collect rent, must have a collection of Title Deeds for each Property, must be able to sell Properties to a Player, must be able to auction a Property, must be able to mortgage properties, must be able to pay $200 to Players that land on or pass the Go Board space, must be able to receive money from Players as directed by Community Chest, Chance cards, Luxury Tax, and other payments Players may have to make. Must maintain a collection of 32 Houses and 32 Hotels and have the ability to sell and buy Houses and Hotels. Banker cannot sell a House or Hotel if all 32 of them have already been sold. | 5 | Sydney
Task: Create Banker class |  | Sydney | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Task: Add private attributes money, TitleDeedDeck, etc. |  | Sydney | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Task: Add methods to get/test information about Banker attributes |  | Sydney | Complete | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
Task: Add rules enforced by Banker: Pay $200 for passing Go, Only sells 32 Houses & 32 Hotels total, Make money Double.POSITIVE_INFINITY |  | Sydney | Complete | 3.5 | 3.5 | 1.5 | 1 | 0.5 | 0 | 0
Task: Test to check that the rules are properly enforced |  | Sydney | Complete | 2.5 | 2.5 | 1 | 1 | 0.5 | 0 | 0
US016: Property Title Deed Cards is a deck of cards that contain all information regrading a property, such as, Color, Name, Basic Rent, Number of Houses, Number of Hotels, Rent with 0 – 4 houses, Rent with Hotel, Mortgage Value, House purchase cost, Hotel purchase cost, whether or not the Property is mortgaged, and the cost to un-mortgage the property. | 5 | Sydney
Task: Create TitleDeedDeck Class (+ TitleDeedCards class?) |  | Sydney | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Task: Add private attributes for color, name, rent, etc. (PropertySpace class Constructor). Association with landOn() method. Use ArrayList to hold rent information, index represents number of houses, same with hotels |  | Sydney | Complete | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Task: Add methods to get/test information about Title Deed Card attributes |  | Sydney | Complete | 3 | 1 | 1 | 0 | 0 | 0 | 0
US011: Implement a Player's turn. Each step in a Player's turn should be implemented independently of all other steps. | 7.5 | Jon
Task: Determine and implement necessary processes for players turn |  | Jon Walsh | Completed | 3 | 2 | 3 | 2 | 1 | 0 | 0
Task: Design action class for turn process |  | Jon Walsh | Completed | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0
Task: implement flexible design for player turn process |  | Jon Walsh | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0
Task: Add documentaton, test all possible method usages and edge cases. |  | Jon Walsh | Completed | 1 | 2 | 2 | 2 | 1.5 | 1 | 0
US020: The Game State has a Game Board, collection of 2 - 4 Players, Dice, and a Banker. The Game State initializes a new game by creating a Game Board, creating a Banker, creating all Players (including the somputer simulated Player), allow each Player to choose a Token, and allocating $1,500 from the Bank to each Player. | 8 | Jon
Task: Design and implement class structure for GameState and make skeleton class |  | Jon Walsh | Completed | 3 | 3 | 3 | 2 | 1 | 0 | 0
Task: Design and implement initializaiton process and validation of game starting. |  | Jon Walsh | Completed | 1 | 1 | 2 | 2 | 1 | 0 | 0
Task: Determine process of game events and how to address events in order. |  | Jon Walsh | Completed | 3 | 3 | 3 | 2 | 1.5 | 1 | 0
Task: Implement main to test and use it to test cases. Also test all methods individually. |  | Jon Walsh | Completed | 1 | 1 | 1 | 1 | 0.5 | 0.25 | 0
TOTAL |  |  |  | 33.625 | 29.75 | 23.25 | 12 | 6.5 | 1.5 | 0