## Sprint Goal
Sprint 1 Goal
Implement the Model for the Game Board.

## Sprint 3 Backlog
AGILE SPRINT 3 BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | SPRINT REVIEW
US 17: Implement Houses. A House should have an icon that represents it. | Small |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Task Refactoring Banker and Player class prior to implementation |  | Sean, Sydney, Jon | Complete | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Design functionality for buying, selling, and registering houses |  | Jon | Complete | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Implement new design into repo |  | Sean, Sydney, Jon | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Write tests to test functionality and expected use later on in the sprint |  | Jon | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 18: Implement Hotels. A Hotel should have an icon that represents it. | Small
Task Refactoring Banker and Player class prior to implementation |  | Sean, Sydney, Jon | Complete | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Design functionality for buying, selling, and registering hotels |  | Jon | Complete | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Implement new design into repo |  | Jon, Sydney, Sean | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Write tests to test functionality and expected use later on in the sprint |  | Jon | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US 11: Implement a Player's turn. Each step in a Player's turn should be implemented independently of all other steps. | Medium
Task Identify player responsibilities that need to be seperated |  | Sydney | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Task Seperate responsibilities into respective methods |  | Jon | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Task Set aside list of buttons needed later on for a player |  | Sean | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Task Update Player tests for new orientation of class |  | Sydney | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US 21: The Computer Controlled Player will simulate the actions of a Human Player. It will make decisions based on Random Numbers and set percentages. It will have several strategies depending on its current state that can be changed dynamically. | Large
Task Identify the parts of the player behavior to randomize |  | Sean | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Task Copy over old HumanPlayer Behavior to ComputerPlayer class |  | Jon | Complete | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0
Task Implement automation of behavior/turn |  | Sean | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0
Task Implement randomization |  | Sydney | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
Task Test behavior with mock testing. |  | Sydney | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0.5 | 0
US 22: The GUI will display the current state of the game (draw the board, player information, display dice roll, display drawn Community Chest and Chance Cards) and allow Players to perform actions that they are allowed. It should indicate the Player whose turn it is and provide buttons (or other GUI components) that guild each player through the sequence of actions allowed for their turn. It should display the tokens for each player and move them around the board accordingly. Each Property space that can be bought must display the player that owns the space. | Large
Task: Design over all GUI for a game and determine orientation of parts of it |  | Sydney, Sean | Complete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task: Use SceneBuilder to construct and format a FXML file for the GUI |  | Sydney | Complete | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task: Seperate parts of the gui into different FXML files, and make them run on one main scene |  | Jon | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Task: Organize the Game board part of the GUI |  | Sean, Jon | Incomplete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task: Organize the player interface part of the gui and property ownership |  | Sydney, Jon | Incomplete | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task: Add controller classes and event listeners for buttons and components |  | Jon | Incomplete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 3 | 2 | 0
Task: Be able to display tokens on the board and move them in source code |  | Jon | Incomplete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 3 | 2 | 0
Task: Be able to display houses and hotels on property spaces |  | Jon | Incomplete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 3 | 2 | 0
TOTAL |  |  |  | 45.6 | 45.6 | 45.6 | 47.6 | 47.6 | 49.6 | 46.6 | 36.6 | 30.6 | 30.1 | 18.6 | 20 | 17 | 10 | 6.5 | 0 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
Add rows and columns as needed.
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0